## Test Cases
Project Name : Sythesis II

Submitted By Vibhunsa
Date of submission for testing : 19-12-2018		Test Cases
Module Name : Store, Terminal

Test Case ID	Test Description	Test Steps	Test Data	Expected Results	Actual Results	Pass/Fail
	Admin(Store)
1	To Check Store link	1)Go to Website	Enter Valid Url	System should open "Manage Store" page	As Expected	Pass
		http://synthesis.weblivelink.com
		2)Log in
		3)Click on Setting module
		4)Click on Store

2	To Check Edit/Upadte Button	1)Go to Website	Enter Valid Url	System should update the record	As Expected	Pass
		http://synthesis.weblivelink.com
		2)Log in
		3)Click on Setting module
		4)Click on Store
		5)Click on Edit
		6)Update ther record
3	To Check Save Button	1)Go to Website	Enter Valid Url	System should Update the reocrd and display	As Expected	Pass
		http://synthesis.weblivelink.com	Store Name= Test,	validatoin message
		2)Log in	Address1= "addr11223#",
		3)Click on Setting module	Mobile =(121)-233-234
		4)Click on Store	Data Proveder = Monali Surve
		5)Enter Store Name in “Store Name” Field	Owner = ankita
		6)Enter Address1 in "Address1"
		7)Enter Mobile No in the “Mobile” Field
		8)Alpha Key And Arrow key Check
		9) Store manager Dropdown Check
		10)Owner Dropdown Check
		11)Click on Save

4	To Check Cancel Button	1)Go to Website	Enter Valid Url	System should redirect to Mange Store page	As Expected	Pass
		http://synthesis.weblivelink.com	Store Name= Test,	withought Saving the Record
		2)Log in	Address1= "addr11223#",
		3)Click on Setting module	Mobile =(121)-233-234
		4)Click on Store	Data Proveder = Monali Surve
		5)Enter Store Name in “Store Name” Field	Owner = ankita
		6)Enter Address1 in "Address1"
		7)Click on Cancel

5	To Check Delete Button	1)Go to Website	Enter Valid Url	System should poop up Message.	As Expected	Pass
		http://synthesis.weblivelink.com
		2)Log in
		3)Click on Setting module
		4)Clilck on Delete Icon

6	To Check Detail Button	1)Go to Website	Enter Valid Url	Syatem should display Store Detail Page	As Expected	Pass
		http://synthesis.weblivelink.com
		2)Log in
		3)Click on Setting module
		4)Click on Detail button

7	To Check Add Terminal tittle on Grid	1)Go to Website	Enter Valid Url	System should display title "Terminals"	System fails to display tittle	Fail
		http://synthesis.weblivelink.com			as "Terminals" on Grid
		2)Log in
		3)Click on Setting module
		4)Observe Add terminal tittle

8	To Check tittle on Add Terminal Page	1)Go to Website	Enter Valid Url	System should display the tittle "Add Terminal"	System fails to display title as	Fail
		http://synthesis.weblivelink.com			"Add Terminal"
		2)Log in
		3)Click on Setting module
		4)obser the title on Add Terminal page

	Admin(Store Terminal)

9	To Check Label on the Menu Bar	1)Go to Website	Enter Valid Url	System should diplay title according to Mennu	System displays"Manage Store"
		http://synthesis.weblivelink.com			Store Terminal"
		2)Log in
		3)Click on Setting module
		4)Hover on Setting Manu.

10	To Check Mange Store Terminal Link	1)Go to Website	Enter Valid Url	System should open Manage Store Terminal Page	As Expected	Pass
		http://synthesis.weblivelink.com
		2)Log in
		3)Click on Setting module
		4)Click on Store Terminal

11	To Check Edit Functionality	1)Go to Website	Enter Valid Url	System should update the record	As Expected	Pass
		http://synthesis.weblivelink.com
		2)Log in
		3)Click on Setting module
		4)Click on Store Terminal
		5)Click on Edit icon
		6)Click on Save

12	To Check lable on Edit Store Terminal Page	1)Go to Website	Enter Valid Url	System should diplay title as "Edit Store Terminal "	System fails todisplays proper	Fail
		http://synthesis.weblivelink.com			tittle as "Edit Store Terminal"
		2)Log in
		3)Click on Setting module
		4)Click on Store Terminal
		5)Click on Edit icon
		6)To Check title on Edit Store Terminal page

13	To Check delete button	1)Go to Website	Enter Valid Url	System should delete the record	As Expected	Pass
		http://synthesis.weblivelink.com		Sytem fials to display messge for delete
		2)Log in
		3)Click on Setting module
		4)Click on Store Terminal
		5)Clcik on delete icon on the Grid

14	To Chek Mange Stoe Terminal Grid	1)Go to Website	Enter Valid Url	System shows data on the grid properly	As Expected	Pass
		http://synthesis.weblivelink.com
		2)Log in
		3)Click on Setting module
		4)Click on Store Terminal
		5)Observe the Grid

15	To Check Name search button.	1)Go to Website	Enter Valid Url	Text field should be rounded and innertext should	System fails to display	Fail
		http://synthesis.weblivelink.com		be Terminal	inner text and rounded corner
		2)Log in			text field.
		3)Click on Setting module
		4)Click on Store Terminal

## BugReport
Project : Sythesis II
				Bug Report

	Bug Name	Test Case Id	Bug Page	Area Path	URL	Status	Priority	Severity	Platform/OS/Browser	Reported On	Reported By	Assigned To	Solved

1	System fails to display tittle	7	Manag Store	LogIn(Admin)>Settings>Store	http://synthesis.weblivelink.com/Admin/store	New	Medium	Moderate	PC/Windows/Crome	20/Dec/18	Pratik	Vibhunsha	Done
	as "Terminals" on Grid

2	System fails to display title as	8	Add Terminal(Store)	Log In(Admin)>Settings>Store>Add Termial	http://synthesis.weblivelink.com/Admin/StoreTerminal/Create/11	New	Medium	Moderate	PC/Windows/Crome	20/Dec/18	Pratik	Vibhunsha	Done
	"Add Terminal"

3	System fails todisplays proper	12	Mange StoreTerminal	Log In(Admin)>Settings> Manage Store	http://synthesis.weblivelink.com/Admin/storeterminal	New	Medium	Moderate	PC/Windows/Crome	20/Dec/18	Pratik	Vibhunsha	Done
	tittle as "Edit Store Terminal"			Termials >Edit

4	System fails to display	15	Mange StoreTerminal	Log In(Admin)>Settings> Manage Store	http://synthesis.weblivelink.com/Admin/storeterminal	New	Medium	Moderate	PC/Windows/Crome	20/Dec/18	Pratik	Vibhunsha	Done
	inner text and rounded corner			Termials
	text field.